## Total
| Title | Location | 16-17 | 17-18 | 18-19 | 19-20 | 20-21 | 21-22 | 22-23 | 23-24 | 24-25 | 25-26 | Proj. Total
Coffin
Life safety | Additions & Renovations | Coffin | 21-22: 30000000 | 30000000
| Upgrade sprinkler system | Coffin | 16-17: 125000 | 125000
| Upgrade fire alarm system | Coffin | 16-17: 100000 | 100000
ADA | ADA restroom renovations | Coffin | 16-17: 150000; 17-18: 150000; 18-19: 100000 | 400000
|  | Coffin | [10 empty] | 0
Structural | Roofing enhancements | Coffin | 16-17: 101500 | 101500
|  | Coffin | [10 empty] | 0
Systems | Electrical systems | Coffin | 18-19: 100000; 19-20: 100000 | 200000
| Plumbing systems | Coffin | 18-19: 100000; 19-20: 100000 | 200000
| Install ventilation in café & gym | Coffin | 16-17: 150000 | 150000
|  | Coffin | [10 empty] | 0
Exterior | Roofing repair/replaced | Coffin | 19-20: 155000; 20-21: 304000; 21-22: 159000 | 618000
|  | Coffin | [10 empty] | 0
HazMat | Transite & asbestos/new trim | Coffin | 16-17: 170500; 17-18: 100000 | 270500
| Lead pint | Coffin | 17-18: 80000 | 80000
| PCB abatement and recaulk | Coffin | 17-18: 210000 | 210000
|  | Coffin | [10 empty] | 0
Finishes | New flooring (asbestos) | Coffin | 16-17: 115500; 17-18: 100000 | 215500
| New ceilings & lighting | Coffin | 18-19: 100000; 19-20: 100000 | 200000
| New wall surfaces | Coffin | 18-19: 200000; 19-20: 200000 | 400000
| New window systems | Coffin | 17-18: 100000; 18-19: 100000; 19-20: 100000 | 300000
|  |  | 18-19: 100000; 19-20: 100000 | 200000
|  | Coffin | [10 empty] | 0
Grounds | * Playground improvements | Coffin | 17-18: 101800; 18-19: 43900; 19-20: 57400; 20-21: 38600 | 241700
| Site improvements | Coffin | 17-18: 123500; 18-19: 13500 | 137000
| Site lighting | Coffin | 17-18: 138400 | 138400
| * Replace underground heating lines | Coffin | 16-17: 161000 | 161000
Equipment |  | Coffin | [10 empty] | 0
34448600
|  | Coffin Total | 1073500 | 1103700 | 857400 | 912400 | 342600 | 30159000 | 0 | 0 | 0 | 0 | 34448600
HBS
Life Safety |  | HBS | [10 empty] | 0
ADA |  | HBS | [10 empty] | 0
Structural |  | HBS | [10 empty] | 0
Systems |  | HBS | [10 empty] | 0
Exterior |  | HBS | [10 empty] | 0
Finishes |  | HBS | [10 empty] | 0
Grounds |  | HBS | [10 empty] | 0
Equipment |  | HBS | [10 empty] | 0
0
|  | HBS Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
JA
| JA demo and site improvement | J Acres | 16-17: 325000; 17-18: 0 | 325000
| Reboilering/NG Conversion | J Acres | 25-26: 315000 | 315000
640000
|  | J Acres Total | 325000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315000 | 640000
BJHS
Life Safety | Fire alarm system upgrade * | BJHS | 16-17: 140400 | 140400
| Fire sprinkler system upgrades * | BJHS | 16-17: 233090 | 233090
ADA | Pavement repairs and ADA improvemnts | BJHS | 19-20: 150000; 20-21: 150000; 21-22: 150000 | 450000
| Reconfigure student restrooms | BJHS | 18-19: 200000; 19-20: 157500 | 357500
| Reconfigure faculty restrooms | BJHS | 18-19: 150000; 19-20: 150000; 20-21: 150000 | 450000
Structural | Roofing Structure * | BJHS | 16-17: 250900 | 250900
| Security vestibule | BJHS | 17-18: 150000 | 150000
| Elevate and secure floors | BJHS | 16-17: 195000 | 195000
| Additions & Renovations | BJHS | 20-21: 30000000 | 30000000
Systems | Replace public address, phones and clock system | BJHS | 17-18: 209200 | 209200
|  | BJHS | [10 empty] | 0
Exterior | Masonry pointing and sealant | BJHS | 16-17: 150000; 17-18: 150000; 18-19: 150000; 19-20: 150000 | 600000
| Window replacements | BJHS | 17-18: 200000; 18-19: 200000 | 400000
| Exterior door replacements | BJHS | 19-20: 100000 | 100000
| Roofing repair/replace | BJHS | 18-19: 343500; 19-20: 324500 | 668000
Hazmat | Remove PCBs | BJHS | 17-18: 168500; 18-19: 150000 | 318500
|  | BJHS | [10 empty] | 0
Finishes | Building wide ceiling and lighting | BJHS | 19-20: 150000; 20-21: 150000; 21-22: 150000 | 450000
Grounds |  | BJHS | [10 empty] | 0
|  | BJHS | [10 empty] | 0
Equipment |  | BJHS | [10 empty] | 0
34972590
|  | BJHS Total | 969390 | 877700 | 1193500 | 1182000 | 30450000 | 300000 | 0 | 0 | 0 | 0 | 34972590
BHS
Life Safety |  | BHS | [10 empty] | 0
ADA |  | BHS | [10 empty] | 0
Structural |  | BHS | [10 empty] | 0
Systems | Theater HVAC | BHS | [10 empty] | 0
Exterior |  | BHS | [10 empty] | 0
Finishes |  | BHS | [10 empty] | 0
Grounds | Egress Road | BHS | 24-25: 500000 | 500000
| Complete Track Resurface | BHS | 16-17: 500000 | 500000
| Additional tennis courts | BHS | 25-26: 208060 | 208060
|  | BHS | [10 empty] | 0
Equipment |  | BHS | [10 empty] | 0
1208060
|  | BHS Total | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 208060 | 1208060
HAW
|  | Hawthorne | [10 empty] | 0
0
|  | Hawthorne Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SYS Wide
| Projects less than $150K | Sys Wide | 1428799 | 1025150 | 895135 | 777950 | 564650 | 416650 | 306650 | 181950 | 154650 | 232950 | 5984534
Equipment |  | Sys Wide | [10 empty] | 0
5984534
|  | Sys Wide Total | 1428799 | 1025150 | 895135 | 777950 | 564650 | 416650 | 306650 | 181950 | 154650 | 232950 | 5984534
R10
| R10 Master Plan | R10 | 16-17: 3400000 | 3400000
3400000
|  | R10 Total | 3400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400000
BGT
|  | BGT | [10 empty] | 0
| Bus Garage Relocation | Bus Garage | 21-22: 2200000 | 2200000
2200000
|  | BGT Total | 0 | 0 | 0 | 0 | 0 | 2200000 | 0 | 0 | 0 | 0 | 2200000
Trans
| School Buses | Trans | 180000 | 185400 | 190962 | 196691 | 202592 | 208669.76 | 214929.8528 | 221377.7484 | 228019.0808 | 234859.6533 | 2063501.0953
2063501.0953
|  | Trans Total | 180000 | 185400 | 190962 | 196691 | 202592 | 208669.76 | 214929.8528 | 221377.7484 | 228019.0808 | 234859.6533 | 2063501.0953
|  | Yearly Total | 7876689 | 3191950 | 3136997 | 3069041 | 31559842 | 33284319.76 | 521579.8528 | 403327.7484 | 882669.0808 | 990869.6533 | 84917285.0953
NOTES:
Scope of Egress Road:
This project constructs a 2 lane access road from BHS to Pleasant Hill Rd. Construction cost and estimate for land acquisition.
Reconstruction of Pleasant Hill Rd, lighting and other amenities not included.
Note on I3: Paul Caron: Placeholder pending renovation plan.
Note on D16: Paul Caron: Combined with flooring on the project worksheet
Note on E16: Paul Caron: Combined with flooring on worksheet
Note on D20: Paul Caron: Combined with asbestos on worksheet
Note on E20: Paul Caron: Combined with asbestos on worksheet
Note on M46: Paul Caron: Pending outcome of Master Plan II.
Note on L80: smckernan: Inc to $400k per Dave 5/8/06 increase to $500k per JE to acknowledge some cost for land acquisition.

## Minor
Coffin | Title | Location | 16-17 | 17-18 | 18-19 | 19-20 | 20-21 | 21-22 | 22-23 | 23-24 | 24-25 | 25-26 | Proj. Total
Life safety | Classroom egress doors | Coffin | 16-17: 40000; 17-18: 0; 20-21: 0 | 40000
| ADA & security hdwe. | Coffin | 16-17: 43500; 17-18: 0; 20-21: 0 | 43500
| Fire Alarm Upgrade | Coffin | 17-18: 90000; 18-19: 0; 19-20: 0 | 90000
| Roofing PM | Coffin | 16-17: 2800 | 2800
ADA | ADA interior signage | Coffin | 17-18: 5000 | 5000
| Life skills toilet rooms | Coffin | 19-20: 50000 | 50000
| Replace ramps/stairs portables | Coffin | 16-17: 15000 | 15000
| Provide ADA drinking fountains | Coffin | 16-17: 50000 | 50000
Structural | Reinforce roof structure | Coffin | 16-17: 77000 | 77000
| Fire seal walls and ceilings | Coffin | 16-17: 35000 | 35000
| Relocate data closet | Coffin | 16-17: 75000 | 75000
Systems | Replace phone system | Coffin | 17-18: 50000 | 50000
| Replace PA system | Coffin | 18-19: 47000 | 47000
| Replace CCTV system | Coffin | 18-19: 53000 | 53000
| Access controls install/PM | Coffin | 15000 | 1000 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 20000
| Increase/maintain access controls | Coffin | 16-17: 10000; 17-18: 5000 | 15000
| Install ventilation in copier rooms | Coffin | 19-20: 16000 | 16000
| Install AC in computer lab | Coffin | 16-17: 16000 | 16000
| Replace clock system | Coffin | 20-21: 39000 | 39000
| Provide power/data at projectors | Coffin | 21-22: 13200 | 13200
| Provide fiber optics to data closets | Coffin | 21-22: 10500 | 10500
| Provide new ceiling/lighting in kit/café | Coffin | 22-23: 41000 | 41000
| HVAC equipment updates | Coffin | [10 empty] | 0
| Ductwork cleaning & PM | Coffin | 18-19: 10000 | 10000
Exterior | Provide eave overhangs | Coffin | 16-17: 35000 | 35000
| Repoint brick veneer | Coffin | 16-17: 20000 | 20000
| Seal masonry | Coffin | 16-17: 10000; 17-18: 10000; 18-19: 10000; 19-20: 10000 | 40000
| Exterior signage | Coffin | 17-18: 2000 | 2000
| Seal egress doorways | Coffin | 17-18: 20000 | 20000
| Demo existing portables | Coffin | 16-17: 32000 | 32000
| Lease 2 double portable buildings | Coffin | 37200 | 37200 | 37200 | 37200 | 37200 | 37200 | 37200 | 37200 | 37200 | 37200 | 372000
| **'Site, heating, power, plumbing | Coffin
| **CCTV, access and fire | Coffin
| Sie lighting | Coffin
| Ramp and steps for portables(leased) | Coffin | 16-17: 5000 | 5000
| Fire alarm connection for portable | Coffin | 16-17: 3000 | 3000
| Access & CCTV for portables | Coffin | 16-17: 4000 | 4000
| Systems, power, data, phone | Coffin | 16-17: 5000 | 5000
| Investigate sewer systems | Coffin | 16-17: 24000 | 24000
| Roofing replacement | Coffin | 17-18: 76000; 25-26: 13000 | 89000
Finishes | Replace wire glass | Coffin | 18-19: 16000 | 16000
| Window treatments | Coffin | 17-18: 15000; 18-19: 15000; 19-20: 15000 | 45000
| Painted finishes | Coffin | 16-17: 10000; 17-18: 10000; 18-19: 10000; 19-20: 10000; 20-21: 10000 | 50000
| Casework/cubbies | Coffin | 20-21: 20000; 21-22: 20000; 22-23: 20000 | 60000
Grounds | Play area drainage | Coffin | 16-17: 13500 | 13500
| Playground chips | Coffin | 16-17: 3000; 18-19: 3000; 20-21: 3000; 22-23: 3000; 24-25: 3000 | 15000
| Playground improvements | Coffin | [10 empty] | 0
| Pavement upgrades | Coffin | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 | 50000 |  |  | 400000
| Build ramps for 2 portables | Coffin | bar: 16-17
Equipment | Custodial equipment | Coffin | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 30000
2094500
|  | Coffin Total | 634000 | 374200 | 254700 | 191700 | 162700 | 134400 | 154700 | 90700 | 43700 | 53700 | 2094500
HBS
Life Safety |  | HBS | [10 empty] | 0
ADA |  | HBS | [10 empty] | 0
Structural | Roofing PM | HBS | [10 empty] | 0
|  | HBS | [10 empty] | 0
Systems | Honeywell controls replacement | HBS | [10 empty] | 0 | bar: 16-17
| Increase/maintain access controls | HBS | 19-20: 5000 | 5000
| HVAC equipment updates | HBS | [10 empty] | 0
| Heat Pump repair/replacements | HBS | [10 empty] | 0
| Heat pump motor repair/replacement | HBS | [10 empty] | 0
| Access controls install/PM | HBS | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 5000
Exterior | Window Glass replacements | HBS | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 5000 | 50000
Finishes | Gym floor finish | HBS | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 35000
Grounds | Repaint playground surfaces | HBS | 16-17: 21200 | 21200
| Playground chips | HBS | 17-18: 3000; 19-20: 3000; 21-22: 3000; 23-24: 3000; 25-26: 3000 | 15000
| Playground improvements | HBS | [10 empty] | 0
| Concrete sealant | HBS | 16-17: 19800; 18-19: 20000; 20-21: 20000; 22-23: 20000; 24-25: 20000 | 99800
Equipment | Custodial equipment | HBS | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 30000
261000
|  | HBS Total | 53000 | 15000 | 32000 | 20000 | 32000 | 15000 | 32000 | 15000 | 32000 | 15000 | 261000
JA
| Replace Flooring | JAcres | [10 empty] | 0
| Roofing PM | Jacres | 16-17: 2800 | 2800
| Upgrade Fire Alarm System | JAcres | 19-20: 68000 | 68000
| building Wide Sprinkler Installation | JAcres | 19-20: 100000 | 100000
170800
|  | JAcres Total | 16-17: 2800; 17-18: 0; 18-19: 0; 19-20: 168000; 20-21: 0 | 170800
BJHS
Life safety | Func Skills Code Compliance | BJHS | 16-17: 25000 | 25000
| Fire seal entrance doors | BJHS | 24-25: 1000 | 1000
| Replace stairwell doors w/fire rated | BJHS | 23-24: 6000 | 6000
| Upgrade fire doors and partitions | BJHS | 24-25: 35000 | 35000
| Replace exit signs | BJHS | 23-24: 10000 | 10000
| Install fire rated partition at M.O./corr. | BJHS | 25-26: 10000 | 10000
| Install safety rails at stairs | BJHS | 25-26: 12000 | 12000
| Verify & fireseal over all partitions | BJHS | 24-25: 10000 | 10000
| Install temperd glass in main stairwell | BJHS | 24-25: 4000 | 4000
ADA | Add ADA signage throughout | BJHS | 22-23: 10000 | 10000
| Update hdwe to access & ADA | BJHS | 16-17: 56550 | 56550
| Provide ADA drinking fountains | BJHS | 16-17: 50000 | 50000
Structural | Roof curbs | BJHS | 16-17: 71500 | 71500
| Infill classroom egress doors | BJHS | 17-18: 9100 | 9100
| Roofing PM | BJHS | 16-17: 2800 | 2800
Systems | Boiler house heating feed | BJHS | 16-17: 75400 | 75400
| Replace ceiling slat/light systems | BJHS | 17-18: 87100 | 87100
| Access controls install/PM | BJHS | 21300 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 25800
| Increase/maintain access controls | BJHS | 16-17: 10000; 17-18: 5000 | 15000
| Upgrade emergency eye/showers | BJHS | 22-23: 35000 | 35000
| Add ventilation on faculty copiers | BJHS | 22-23: 6000 | 6000
| Emergency generator | BJHS | 19-20: 50000 | 50000
| Technology outlets, wiring | BJHS | 21-22: 20000 | 20000
| Fiber optics expansion | BJHS | 21-22: 20000 | 20000
| HVAC equipment updates | BJHS | [10 empty] | 0
| Ductwork cleaning & PM | BJHS | 19-20: 20000 | 20000
| Replace CCTV system | BJHS | 19-20: 94000 | 94000
Finishes | Replace wire glass throughout | BJHS | 25-26: 54000 | 54000
| Replace Flooring | BJHS | 17-18: 40000; 18-19: 40000 | 80000
| Provide new flooring in abated areas | BJHS | 20-21: 50000 | 50000
| Carpet replacements | BJHS | 19-20: 50000; 20-21: 50000; 21-22: 50000 | 150000
| Paint finishes updates | BJHS | 19-20: 10000; 20-21: 10000; 21-22: 10000; 22-23: 10000; 23-24: 10000 | 50000
| Replace operable partitions | BJHS | 21-22: 30000; 22-23: 30000 | 60000
| Enclose the kiln area | BJHS | 20-21: 7500 | 7500
| Window treatments | BJHS | 20-21: 30000 | 30000
| Install ceiling & lighting music rm | BJHS | 18-19: 10000 | 10000
| Modify sprinklers for music ceiling | BJHS | 18-19: 7500 | 7500
| Update teacher's lounge fixtures | BJHS | 25-26: 15000 | 15000
| New pipe insulation | BJHS | 20-21: 8000 | 8000
| Locker replacements | BJHS | 19-20: 20000; 20-21: 20000; 21-22: 20000 | 60000
| Gym floor finish | BJHS | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 3500 | 35000
| Art room sinks and cabinets | BJHS | 16-17: 20000 | 20000
Hazmat | Remove lead paint and repaint | BJHS | 21-22: 65000 | 65000
| Asbestos Abatement (flooring) | BJHS | 17-18: 40000; 18-19: 40000; 19-20: 40000; 20-21: 30000; 21-22: 30000 | 180000
Exterior |  | BJHS | [10 empty] | 0
| Roofing restoration & replacement | BJHS | 17-18: 117000; 20-21: 30000; 23-24: 15000 | 162000
| Window caulking and reglaze | BJHS | 17-18: 20000 | 20000
| Masonry sealant | BJHS | 16-17: 60049 | 60049
| Exterior door & window signage | BJHS | 17-18: 3000 | 3000
Grounds | Play area improvements | BJHS | 18-19: 58000 | 58000
| Update site lighting | BJHS | 18-19: 25000 | 25000
| Playground improvements | BJHS | [10 empty] | 0
| Storm drainage repair & investigation | BJHS | 18-19: 100000 | 100000
Equipment | Custodial equipment | BJHS | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 30000
2101299
|  | BJHS Total | 399099 | 328200 | 287500 | 291000 | 242500 | 252000 | 98000 | 48000 | 57000 | 98000 | 2101299
BHS
Life Safety |  | BHS | [10 empty] | 0
ADA |  | BHS | [10 empty] | 0
Structural |  | BHS | [10 empty] | 0
| Roofing PM | BHS | 16-17: 3500 | 3500
Systems | Security enhancements/theater doors | BHS | 18-19: 35000 | 35000
| Access controls install/PM | BHS | 19900 | 1000 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 24900
| Plumbing fixture replacements | BHS | 3000 | 2000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 13000
| Water fountain updates | BHS | 16-17: 5000; 18-19: 5000; 20-21: 5000 | 15000
| HVAC equipment updates | BHS | [10 empty] | 0
| Crooker AC repairs | BHS
| Pump station cleaning | BHS | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 5000
Finishes | Seat Replacement-Crooker Theater | BHS | 19-20: 36000; 20-21: 43000 | 79000
| Replace Carpet and Tile | BHS | 16-17: 100000; 17-18: 100000; 18-19: 100000 | 300000
| Replace 100 large lockers /Boys | BHS | 18-19: 35985 | 35985
| Gym floor finish | BHS | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 4000 | 40000
HAZMAT |  | BHS | [10 empty] | 0
Exterior | Roof Life Repairs/replace/extension | BHS | 16-17: 117000; 17-18: 145000; 20-21: 56000 | 318000
| Construct 3 bay garage | BHS | 25-26: 55000 | 55000
| Window sash replacements | BHS | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 10000
Grounds |  | BHS | 19-20: 0; 20-21: 0 | 0
| Front paver sealant | BHS | 16-17: 3500; 18-19: 3500; 20-21: 3500; 22-23: 3500; 24-25: 3500 | 17500
| Back paver sealant | BHS | 16-17: 6200; 18-19: 6200; 20-21: 6200; 22-23: 6200; 24-25: 6200 | 31000
Equipment | Custodial equipment | BHS | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 30000
1012885
|  | BHS Total | 266600 | 256500 | 195685 | 46000 | 123700 | 10000 | 19700 | 10000 | 19700 | 65000 | 1012885
M.O.
Life Safety |  | MO | [10 empty] | 0
ADA |  | MO | [10 empty] | 0
Structural |  | MO | [10 empty] | 0
Systems | Access controls install/PM | MO | 19900 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 22150
| HVAC equipment updates | MO | [10 empty] | 0
Exterior |  | MO | [10 empty] | 0
| Roofing PM | MO | 16-17: 700 | 700
| Roofing repair/replace | MO | 20-21: 1500; 21-22: 4000 | 5500
Finishes |  | MO | [10 empty] | 0
Grounds |  | MO | [10 empty] | 0
Equipment | Custodial equipment | MO | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 10000
38350
|  | Mn Office Total | 21600 | 1250 | 1250 | 1250 | 2750 | 5250 | 1250 | 1250 | 1250 | 1250 | 38350
SYS
| System wide bldg. modifications | Sys Wide | [10 empty] | 0
| Storm Drain and Paving Repair | Sys Wide | 16-17: 50000; 17-18: 50000; 18-19: 60000; 19-20: 60000 | 220000
| Replace pick up truck | Sys Wide | 16-17: 0; 18-19: 40000 | 40000
260000
|  | Sys Wide Total | 50000 | 50000 | 100000 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 260000
BGT
Life Safety |  | BGT | [10 empty] | 0
ADA |  | BGT | [10 empty] | 0
Structural |  | BGT | [10 empty] | 0
Systems |  | BGT | [10 empty] | 0
Exterior |  | BGT | [10 empty] | 0
| Roofing PM | BGT | 16-17: 700 | 700
| Roofing repairs/replacements | BGT | 18-19: 23000; 23-24: 17000 | 40000
Finishes |  | BGT | [10 empty] | 0
Grounds | Playground chips | BGT | 16-17: 1000; 18-19: 1000; 20-21: 1000; 22-23: 1000; 24-25: 1000 | 5000
| Playground improvements | BGT | [10 empty] | 0
Equipment | Custodial equipment | BGT | [10 empty] | 0
45700
|  | Fac/Grds Total | 1700 | 0 | 24000 | 0 | 1000 | 0 | 1000 | 17000 | 1000 | 0 | 45700
| Totals to Page 1 | Yearly Total | 1428799 | 1025150 | 895135 | 777950 | 564650 | 416650 | 306650 | 181950 | 154650 | 232950 | 5984534
Note on B37: Paul Caron: Existing leased portables do not have a ramp
Note on G151: smckernan: Rows 1-5 in front section; 139 seats @ $200. 3/13/2006 Scott can reduce to $27,800

## Renewables
School
Coffin
Exterior
Roof
Windows
Exterior doors
Interior
Ceilings
Walls
Flooring
Lighting
Fixtures
Systems
Electrical
Plumbing
Sprinkler
Fire Alarm
Intrusion
Access
BHS | Ejector pump
HBS | heat pumps
geo field pumps
building geo pumps